## KPK
NON-PERFORMING CONTRACTORS IN KPK (TILL MAY, 2010) (Annexed - A
S. No | Name of contractor | Contract No | Package No | Facilities | Date of commencement | Date of Original Completion | Revised Completion Date i/c EOT(s) if any | Latest Physical Progress Achieved (% age) | Overall Physical Progress (% age) | Planned Progress (% age) | Date on which the physical progress should have been completed | To Date | Lag (% age) | Remarks
1 | M/s A & AC CONSTRUCTION CO | PERRA/Abbottabad/03/2007 | 2 | GGPS Bakote * GGPS Sangal GGMS Aliabad GPS Saranda GPS Aliabad | 2007-06-15 | 2008-06-14 | 2009-08-13 | 0 91 77 91 76 | 67 | 100% | 2008-11-25 07:12 | 2010-05-31 | 51.04% | * Deleted from the scope of work - Recommended for LDs
2 | M/s Akbar Khan | PERRA/KOHISTAN/17/2009 | 12A | GHS Sherakot | 2009-10-09 | 2010-10-08 | 2010-10-08 | 0 | 0 | 64.29% | 2009-10-09 | 2010-05-31 | 64.29%
3 | M/s Allai Construction Co | PERRA/Battagram/30/2008 | 26 | GPS Pitow Nogram | 2009-01-28 | 2010-01-27 | 2010-06-27 | 50 | 50 | 94.76% | 2009-10-12 12:00 | 2010-05-31 | 44.76%
|  | PERRA/Battagram/51/2008 | 55A | GGPS Chaloni | 2009-04-10 | 2010-04-09 | 2010-04-09 | 68 | 68 | 100% | 2009-12-13 12:29 | 2010-05-31 | 40.5%
|  | PERRA/Battagram/71/2009 | KFW-4 | GMS Banna | 2009-12-05 | 2010-12-04 | 2010-12-04 | 2 | 2 | 48.63% | 2009-12-12 06:43 | 2010-05-31 | 46.63%
4 | M/s Ameer Muqaam & Company. | PERRA/Battagram/28/2008 | 34 | GHS Paimal GGMS Sultan Abad GPS Seri Paimal | 2008-12-06 | 2010-12-04 | 2010-04-05 | 61 61 50 | 58 | 100% | 2009-09-13 07:12 | 2010-05-31 | 48%
|  | PERA/Shangla/14/2007 (M/s Ameer Muqaam & Company-CMES JV) | I-B II-B III-A III-B IV-A VI-B VII-A VII-B VIII-A | GPS Garai Kandow GPS Dara Serai GPS Nakhtar GGPS Kohay GPS Alami Banada Martung GPS Mandoria GPS Kankar GPS Kadona GPS Dod Banai GPS Didal GGPS Faiza Bain GGPS Khonan GPS Banj Sanila GGPS Gharai GPS Enawar GGPS Palang Sar GPS Chakisar Kuzpaw GGPS Cheedam GPS Dar kalay GGPS Dandai Chakisar GPS Siknai Kandawgai GMS Said Abad GPS Opal GGPS Langbar No.1 GPS Gali Butt GPS Manga GHS Kuz Karora GPS Gunangar | 2009-03-31 | 2010-03-30 | 2010-03-30 | 35.00 17.00 5 20.00 5 20 20.00 35 5.00 5.00 20.00 20.00 5.00 20.00 20.00 20.00 10.00 5.00 20 35.00 20.00 20.00 5.00 35.00 5.00 20.00 0 5.00 | 18 | 100% | 2009-06-04 12:29 | 2010-05-31 | 84.62%
|  | PERRA/GOV-Shangla/02/2008 | 2 | Police Post, Olandar | 2009-05-04 | 2010-05-04 | 2010-05-04 | 18 | 18 | 100% | 2009-07-08 16:48 | 2010-05-31 | 83.24%
|  | Paimal Rangeenabad Road | Single Package | Paimal Rangeenabad Road | 2008-11-25 | 2009-11-24 | 2009-11-24 | 72 | 72 | 100% | 2009-08-14 01:55 | 2010-05-31 | 52.52%
|  | PERRA/GOV-Shangla/02/2008 | 2 | Police Post, Olandar | 2009-05-04 | 2010-05-04 | 2010-05-04 | 18 | 18 | 100% | 2009-07-08 16:48 | 2010-05-31 | 83.24%
5 | M/s Amin & Co | PERRA/Shangla/07/2007 | 5-A&5-B | *GPS Maira GHS Maira | 2008-07-25 | 2009-07-24 | 2009-07-24 | 0 31 | 31 | 100% | 2008-11-14 20:10 | 2010-05-31 | 83.28% | *Land issue on GPS Maira - Recommendations for imposition of LDs are sent to Client vide our letter No. 2778/334/JK/11-A/11294 dated 17/2/10
6 | M/s Anwar & Brothers | PERRA/Abbottabad/05/2007 | 6A | GPS Namal GGPS Bandian GGPS Tarrach * GPS Chaleesan GPS Majuhan GPS Nara GPS Tarrach GGPS Lower Kurli GGPS Upper Kurli GGPS Garhi Nambal | 2007-06-13 | 2008-06-12 | 2009-06-25 | 83 94 0 30 59 86 95 21 61 61 | 59 | 100% | 2008-08-24 08:53 | 2009-10-30 | 49.61% | * Deleted from the scope of work - Recommended for LDs
7 |  | PERRA/Abbottabad/11/2007 | 15A | GPS Rahi GPS Kund Battal GMS Bathian GPS Malmoolla GPS Baseera | 2007-11-20 | 2008-11-19 | 2008-11-19 | 65 95 78 95 22 | 71 | 100% | 2008-08-05 03:36 | 2009-10-30 | 63.5% | Recommended for LDs
8 | M/s Arif Khan & Bros | PERRA/Kohistan/02/2007 | 6-A | GPS Galgan GPS Sangai | 2007-09-21 | 2008-09-20 | 2009-09-23 | 31 28 | 29 | 100% | 2008-04-20 13:41 | 2010-05-31 | 78.38% | LDs imposed vide employer Letter No 063/1-G Dated 10-03-2010
|  | PERRA/Kohistan/06/2007 | 3 | GMS Badakot GPS Bataira Pain GPS Batal Harran GMS ParaGari Harran GPS Nasro GPS Baila Sali Khail | 2007-09-21 | 2008-09-20 | 2009-10-03 | 12 30 8 1 1 1 | 9 | 100% | 2007-11-26 20:53 | 2010-05-31 | 93.2% | LDs imposed vide employer Letter No 063/1-G Dated 10-03-2010
|  | PERRA/Kohistan/07/2007 | 2 | GPS Ashial Seo GPS Kai Rustam Abad GPS Kai Sher Seo GPS Ramal | 2007-07-21 | 2008-07-20 | 2008-07-20 | 30 31 70 20 | 38 | 100% | 2007-12-06 16:48 | 2010-05-31 | 86.73% | LDs imposed vide employer Letter No 063/1-G Dated 10-03-2010
|  | PERRA/Kohistan/08/2007 | 4 | GGMS Guli Bagh | 2007-09-21 | 2008-09-20 | 2008-09-20 | 5 | 5 | 100% | 2007-10-09 06:00 | 2010-05-31 | 98.14% | LDs imposed vide employer Letter No 063/1-G Dated 10-03-2010
|  | PERRA/Kohistan/13/2007 | 6C | GHS Pattan | 2007-12-01 | 2008-12-01 | 2010-07-13 | 13 | 13 | 95.5% | 2008-04-03 03:36 | 2010-05-31 | 82.5% | N/A
9 | M/s ARIFULLAH JAN& CO | PERRA/Abbottabad/36/2007 | 25A | GHS Chamiali | 2008-04-30 | 2009-04-29 | 2010-01-01 | 47 | 47 | 100% | 2009-02-11 04:05 | 2010-05-31 | 62.26% | Recommended for LDs
10 | M/s Bashir Ahmad | PERRA/Abbottabad/66/2008 | 32A | GHS Mirpur | 2009-05-02 | 2010-05-01 | 2010-05-01 | 28 | 28 | 100% | 2009-08-11 22:05 | 2010-05-31 | 74.13% | Recommended termination
11 | M/s Competent PEB SFAN Consortium | PEERA/Shangla/18/2008 | VI-A VI-B VII-A VII-B VIII-A VIII-B | GGPS Shang GGPS Molsar GGPS Gandorai Kormung GPS Dand Pir Abad GMS Kormung GMS Lahor GPS Kadona GPS Khawar Karin GPS Siddique GGPS Bar Kana GGPS Chelai Qalagai GPS Karshat GPS Kerai Larai GPS Olander GPS Sar Banda No.1 GPS Dherai Olander GPS Basi GGPS Dawalat Kalay GPS Banr Sangrai GPS Larai Lilwanai GMS Banr GGPS Ghundoo GPS Barkas Pagorai GPS Shalmano Mian Kalay GGPS Mata Banjar GPS Bahram Darra GPS Shalmano Kotkay | 2009-03-31 | 2010-03-30 | 2010-03-30 | 20% 20% 5% 20% 20% 20% 5% 20% 20% 20% 20% 20% 5% 20% 5% 5% 20% 20% 20% 5% 20% 5% 20% 20% 20% 5% 20% | 16 | 100% | 2009-05-28 05:46 | 2010-05-31 | 86.33%
12 | M/s Darwaish Engineerings & Co | PERRA/Abbottabad/46/2008 | 57A | GHS Dhamtor | 2008-06-17 | 2009-06-16 | 2010-01-10 | 44 | 44 | 100% | 2009-02-23 16:19 | 2010-05-31 | 64.7%
13 | M/s Faiz ur Rehman & co | PERRA/Shangla/16/2007 | 1-A | GGHS Aloch | 2008-01-28 | 2009-01-27 | 2009-11-13 | 56 | 56 | 100% | 2009-01-28 19:12 | 2010-05-31 | 57.05% | Recommendations for imposition of LDs are sent to Client vide our letter No. 2778/334/JK/11-A/11294 dated February 17,2010
|  | PERRA/Shangla/10/2007 | 6-B | GMS Shahtoot GGPS Ranyal | 2007-11-12 | 2008-11-11 | 2009-07-27 | 75 85 | 80 | 100% | 2009-03-24 09:36 | 2010-05-31 | 46.47% | For GMS Shahtoot, GGPS Ranyal Recommendations for imposition of LDs are sent to Client vide our letter No. 2778/334/JK/11-A/11294 dated February 17,2010
|  | PERRA/FOREST.01 Shangla/10/2008 | 1 | DFO Residence (Alpurai) RFO Residence Alpurai RFO Residence Korara Head Clerk Quarter (Alpurai) Senior Clerk Quarter(Alpurai) Junior Clerk Quarter (Alplurai) Class IV Quarter (Alpurai) - 1 Class IV Quarter (Alpurai) - 2 Class IV Quarter (Alpurai) - 3 Class IV Quarter (Alpurai) - 4 Class IV Quarter (Alpurai) - 5 Class IV Quarter (Alpurai) - 6 Class IV Quarter (Alpurai) - 7 Rest House Yakhtangi Rest House Opal Kandow | 2009-09-10 | 2010-09-08 | 2010-09-08 | 18 19 19 43 0 14 22 22 22 18 18 5 2 1 0 | 15 | 72.45% | 2009-11-03 10:48 | 2010-05-31 | 57.45%
14 | M/s Fazal Karim & Co. | PERRA/Abbottabad/02/2007 | 5 | GPS DEHRA GGPS JULAIAL GPS LAMIA LARAN GGPS HILL BEROTE GGPS Lahoor Kuss | 2007-05-09 | 2008-05-08 | 2009-04-07 | 90 70 53 69 7 | 58 | 100% | 2008-06-17 10:05 | 2010-05-31 | 63.74% | Recommended for LDs
|  | PERRA/Gov-ABBOTTABAD/08/2007 | Package 04-A/2007 | District Account Office | 2008-02-11 | 2009-02-10 | 2010-06-30 | 50 | 50 | 96.55% | 2009-04-21 | 2010-05-31 | 46.55%
|  | PERRA/GOV-Shangla/05/2008 | 5 | Police Post, Shangla | 2009-04-25 | 2010-04-24 | 2010-04-24 | 1 | 1 | 100% | 2009-04-28 15:22 | 2010-05-31 | 99.09%
|  | PERRA/GOV-Shangla/09/2008 | 9 | Police Post Martung, Puran | 2009-10-24 | 2010-10-23 | 2010-10-23 | 14 | 14 | 60.16% | 2009-12-13 23:02 | 2010-05-31 | 46.16%
15 | M/s Haji Bahadur Sher & Sons | PERRA/GOV/ KOHISTAN/06/2008 | 2 | Police Post Jijal Police Post Kayal | 2009-01-29 | 2010-01-28 | 2010-01-28 | 60 49 | 55 | 100% | 2009-08-17 04:48 | 2010-05-31 | 58.89%
|  | PERRA/Kohistan/ 34/2009 | H-34 | BHU Jijal | 2009-06-11 | 2010-06-10 | 2010-06-10 | 6 | 6 | 97.25% | 2009-07-02 20:10 | 2010-05-31 | 91.25%
16 | M/s Haji Muhammad Anwar | PERRA/KOHISTAN/13/2008 | 9 | GHS Bataira | 2009-01-26 | 2010-01-25 | 2010-01-25 | 20 | 20 | 100% | 2009-04-08 19:12 | 2010-05-31 | 85.14%
17 | M/s Haji Muhammad Ibhram & Co | PERRA/Shangla/ 59/2009 | H-59 | BHU Titwalan | 2009-02-11 | 2010-02-10 | 2010-02-10 | 1 | 1 | 100% | 2009-02-14 15:22 | 2010-05-31 | 99.23%
|  | PERRA/Shangla/ 58/2009 | H-58 | BHU Chowga | 2009-02-11 | 2010-02-10 | 2010-02-10 | 1 | 1 | 100% | 2009-02-14 15:22 | 2010-05-31 | 99.23%
18 | M/s Haji Muhammad Ibrahim & Sons. | PERRA/Battagram/40/2008 | 51-A | 1. GPS Noumanabad 2. GPS Banda Qayyum Khan | 2009-02-11 | 2010-02-10 | 2010-02-10 | 38 36 | 37 | 100% | 2009-06-25 16:19 | 2010-05-31 | 71.59%
19 | M/s Haroon & Co. | PERRA/Mansehra/51/2008 | 73-A | GHS Thakra | 2008-11-22 | 2009-11-21 | 2009-11-21 | 50 50 50 8 | 40 | 100% | 2009-04-16 14:24 | 2010-05-31 | 73.77% | Recommendation for LDs sent to Employer vide letter No 2778/334/JK/11-A/14021 Dated 24-05-2010
20 | M/s Haroon Rashid & Sons | PERRA/Abbottabad/38/2008 | 60A | GHS Havalian No.2 | 2008-06-26 | 2009-06-25 | 2010-01-21 | 60 | 60 | 100% | 2009-06-05 09:36 | 2010-05-31 | 51.08% | Recommended for LDs
|  | PERRA/Abbottabad/39/2008 | 13C | GHS NAWASHER | 2008-03-28 | 2009-03-27 | 2009-03-27 | 73 | 73 | 100% | 2008-12-18 17:17 | 2010-05-31 | 66.53% | Recommended for LDs
21 | M/s Iftikhar Ahmad Khan & Brothers | PERRA/Abbottabad/52/2008 | 86,87,88, 89 | GGPS Talhar GPS Bandi Matrach GPS Pando Thana GGPS Paswal Mian GPS Sial | 2008-10-06 | 2009-10-05 | 2010-01-29 | 65 64 49 58 62 | 60 | 100% | 2009-07-21 | 2010-05-31 | 52.16% | Recommended for LDs
22 | M/s Ihsanullah khan | PERRA/Abbottabad/102/2009 | 53 | GPS Thannah Totani GHS Bhuraj | 2009-08-06 | 2010-08-05 | 2010-08-05 | 32 6 | 19 | 81.87% | 2009-10-14 03:50 | 2010-05-31 | 62.87%
23 | M/s Imperial Construction | PERRA/Battagram/41/2008 | 43-A | 1. GGPS Kaklai Bala 2. GPS Ander Wali Takya | 2009-02-11 | 2010-02-10 | 2010-02-10 | 15 5 | 10 | 100% | 2009-03-19 09:36 | 2010-05-31 | 92.32% | Recommendation for termination sent to client vide our letter No 2778/334/JK/11-A/14149 Dated 31-05-2010
|  | PERRA/Mansehra/18/2007 | 46 | Store at Oghi A.D. Office Oghi | 2009-07-09 | 2010-07-08 | 2010-07-08 | 1 | 1 | 83.79% | 2009-07-12 15:22 | 2010-05-10 | 82.79% | Recommendation for terminationsent to client vide our letter No 2778/334/JK/11-A/13551 Dated 10-05-2010
24 | M/s Inayat Khan & CO | PERRA/ LIVESTOCK.02/ KOHISTAN/06/ 2008 | 11 | Tehsil Veterinary Hospital & Allied Building Pattan | 2009-06-09 | 2010-06-08 | 2010-06-08 | 9 | 9 | 78.02% | 2009-07-11 18:14 | 2010-03-20 | 69.02% | Terminated vide client letter No 9137/4-c Dated 20/03/2010.
25 | M/s Irshad Khan & Co. | PERRA/Man/74/2008 | 56 | GGPS Sikandara GPS Sikandara | 2009-02-14 | 2010-02-13 | 2010-02-13 | 60 55 | 58 | 100% | 2009-09-13 02:53 | 2010-05-31 | 55.18% | Recommendation for LDs sent to Employer vide letter No 2778/334/JK/11-A/14021 Dated 24-05-2010
26 | M/s Jadeed International | PERRA/MANSEHRA/103/2008. | 60B | GPS Damnala GPS Kamar Mary | 2009-04-15 | 2010-04-14 | 2010-04-14 | 45 55 | 50 | 100% | 2009-10-14 | 2010-05-31 | 55.72%
27 | M/s JAMAL MUHAMMAD KHAN & CO | PERRA/Abbottabad/47/2008 | 17C | GPS Havalian No.3 | 2008-05-29 | 2009-05-28 | 2009-09-27 | 77 | 77 | 100% | 2009-06-07 05:17 | 2010-05-31 | 48.88% | Recommended for LDs
|  | PERRA/Abbottabad/67/2008 | 32B | GGHS Malikpura | M/S JAMAL MUHAMMAD KHAN & CO, | 2009-06-18 | 2010-06-17 | 2010-06-17 | 29 | 29 | 95.33% | 2010-05-31 | 2010-05-31 | Recommended for LDs
28 | M/s Kala Dhaka Construction | Man/99/2008 | 75 | GPS Phuldar GPS Baradar | 2009-05-11 | 2010-05-10 | 2010-05-10 | 55 50 | 53 | 100% | 2009-11-19 22:05 | 2010-05-31 | 49.89%
29 | M/s Khan Muhammad Khan | PERRA/Abbottabad/12/2007 | 10A | GGPS Dalola No.1 GGPS Hadora Bandi GGPS Darra GGPS Hadora Khas GPS Chengali GPS Tarkote GPS Dedal GPS Sirla GPS Hadora GPS Dara | 2007-08-01 | 2008-07-31 | 2010-08-27 | 50 38 16 19 14 15 50 16 38 25 | 28 | 92.16% | 2008-06-10 03:50 | 2010-05-31 | 64.16% | i)- First Terminated vide letter No 7599/ I.TE dated 06-11-2009. ii)- Now the contracte has been revived by the client on April 27, 2010.
30 | M/s Lawari Construction | PERRA/MANSEHRA/131/2009 | 144 | GPS Chanial GPS Lubar GPS Parkhaian | 2009-08-27 | 2010-08-26 | 2010-08-26 | 26 28 28 | 27 | 76.1% | 2009-12-03 06:43 | 2010-05-31 | 49.1%
31 | M/s Margala Tuff Tiles | PERRA/Abbottabad/74/2009 | 123 | GGPS Sohlan Payeen | 2009-09-16 | 2010-09-15 | 2010-09-15 | 18 | 18 | 70.6% | 2009-11-20 12:29 | 2010-05-31 | 52.6%
32 | M/s Muhammad Ibrahim & Co. | PERRA/MANSEHRA/85/2008. | N/A | GGHSS Baffa | 2009-05-11 | 2010-05-10 | 2010-05-10 | 60 | 60 | 100% | 2009-12-15 09:36 | 2010-05-31 | 43.27%
33 | M/s Muhammad Irshad & Co | 09/Forest | 09/Forest | Forest Buildings Siran | 2008-11-20 | 2009-11-19 | 2009-11-19 | 60 | 60 | 100% | 2009-06-26 09:36 | 2010-05-31 | 60.79%
34 | M/s Muhammad Naeem & Co. | PERRA/MAN/105/2008. | 70 | GGPS New Darband | 2009-04-17 | 2010-04-16 | 2010-04-16 | 66 65 66 | 66 | 100% | 2009-12-13 05:46 | 2010-05-31 | 41.26%
35 | M/s Muhammad Sadiq & Sons. | PERRA/Abbottabad/53/2008 | 74 | GGPS SATORA GPS SATORA | 2008-11-27 | 2009-11-26 | 2010-02-24 | 47 82 | 64 | 100% | 2009-09-13 13:26 | 2010-05-31 | 47.17% | Recommended for LDs
36 | M/s Muhammad Wahab & Co. | PERRA/MANS EHRA/106/2009 | 69-B | GPS Jiggi Pain | 2009-05-23 | 2010-05-22 | 2010-05-22 | 60 | 60 | 100% | 2009-12-27 09:36 | 2010-05-31 | 41.45%
37 | M/s Munwar Shah & Brothers | PERRA/Kohistan/ 33/2009 | H-33 | BHU Goshali | 2009-06-08 | 2010-06-07 | 2010-06-07 | 3 | 3 | 98.08% | 2009-06-18 22:05 | 2010-05-31 | 95.08%
38 | M/s Munwar Shah & Sons | PERRA/Kohistan/ 27/2009 | H-27 | BHU Soyal Dara | 2009-07-02 | 2010-07-01 | 2010-07-01 | 0 | 0 | 91.48% | 2009-07-02 | 2010-05-31 | 91.48% | Recommendation for termination sent to client for concurrence vide our letter No 2778/334/JK/11-A/12137 Dated 18-03-2010
39 | M/s Pakhal Construction Company | PERRA/Mansehra/69/2008 | 42 | GGPS Granthali GPS Dadar Qadeem GPS Granthali GGPS BAKKI GGPS Sulan Bandi | 2009-01-01 | 2010-01-01 | 2010-01-01 | 100 100 78 58 24 | 72 | 100% | 2009-09-20 19:12 | 2010-05-31 | 48.97% | For GGPS BAKKI Recommendation for LDs sent to Employer vide letter No 2778/334/JK/11-A/14021 Dated 24-05-2010
|  | Perra/Forest.01/BTM/08/2008 | 1 | DFO Residence Battagarm. Range Quarter Battagram. Assistant Quarter Battagram. Senior Clerk Quarter Battagarm. Four Junior Clerk Quarter Battagram. Two Forester Quarter Battagram. One Driver & One Chowkidar Quarter Battagram. Two Chowkidar Quarter Battagram. Two Peon Quarter Battagram | 2008-09-24 | 2009-09-23 | 2009-09-23 | 81 81 76 81 76 76 61 76 74 | 76 | 100% | 2009-06-27 15:22 | 2010-05-31 | 54.94%
40 | M/s Perfect Builder | PERRA/Abbottabad/14/2007 | 14 | GPS Ghari | 2007-12-01 | 2008-11-30 | 2008-11-30 | 51 | 51 | 100% | 2008-06-04 03:36 | 2010-03-09 | 77.55% | Terminated vide letter No 8963/4-C Dated 09-03-2010
41 | M/s Perk Engineering Services | PERRA/Abbottabad/30/2007 | 21B | GHSS RICH BHEN | 2007-12-01 | 2008-11-30 | 2009-07-12 | 77 | 77 | 100% | 2009-02-26 12:43 | 2010-05-31 | 50.27% | Recommended for LDs
42 | M/S Raja Sabir Khan & Co | PERRA/Shangla/ 46/2009 | H-46 | BHU Shekwalai | 2009-02-11 | 2010-02-10 | 2010-02-10 | 1 | 1 | 100% | 2009-02-14 15:22 | 2010-05-31 | 99.23%
43 | M/s Rashid & Brothers | PERRA/Abbottabad/60/2008 | 36 | GPS KOHALIAN | 2008-11-22 | 2009-11-21 | 2010-03-21 | 62 | 62 | 100% | 2009-09-18 01:55 | 2010-05-31 | 45.93% | Recommended for LDs
|  | PERRA/Abbottabad/65/2008 | 79 | GPS Kutla | 2009-06-04 | 2010-06-03 | 2010-06-03 | 22 | 22 | 99.18% | 2009-08-23 01:55 | 2010-05-31 | 77.18%
|  | PERRA/Abbottabad/100/2009 | 76A | GPS Batta Kari | 2009-09-18 | 2010-09-17 | 2010-09-17 | 18 | 18 | 70.05% | 2009-11-22 12:29 | 2010-05-31 | 52.05%
44 | M/s Relief International | PERRA/MANSEHRA/SCIPS/2009 * | SCIPS-1 | GGPS SHAMSABAD GGPS CHAM BHATTI GPS BAKRIAN GPS KANDI HILKOT GPS SHANG RATA GPS HAIR NAROTI GGPS CHARYAN GPS BATTI GPS CHALLUNDRAIN GPS DEVELY GPS SALDHAR NO.1 GPS CHARIAN | 2008-09-10 | 2009-09-09 | 2009-09-09 | 100 100 3 58 58 100 100 73 3 66 52 0 100 | 62 | 100% | 2009-04-23 16:19 | 2010-05-31 | 64.06% | i- Recommendation for LDs sent to Employer vide letter No 2778/334/JK/11-A/14021 Dated 24-05-2010 ii- Possession of around 15 sites still not given to contractor as per Mr. Salman shahid
|  |  |  | GPS HOTAR NARA GGPS SARI SUBIDAR GPS NOGRAM BATTAL GGPS KHAKOO GPS KHAKHOO GGPS HARRORI PAYEEN GGPS KARMANG BALA GPS KUND BALA GGPS KANDO GALI GGPS MALOOKRA BATTAL GPS GALI BALI MANG | 2008-09-10 | 2009-09-09 | 2009-09-09 | 37 52 100 68 59 58 15 52 54 4 56 | 50 | 100% | 2009-03-11 | 2010-05-31 | 71.02%
|  |  |  | GGPS THIRDA BATTAL GPS HILKOT GPS NEEL BAN GPS SHAROTO PHALI GPS SATHAN GALI GPS TREADDA GPS HOLA GPS BAYAN GGPS ASHWAL | 2008-09-10 | 2009-09-09 | 2009-09-09 | 3 0 3 0 4 0 37 3 49 | 11 | 100% | 2008-10-20 00:58 | 2010-05-31 | 93.62%
|  |  |  | GPS GALI GADDA GPS MALKAN GPS KHAN GPS SERI BALA GPS CHATTAR PLAIN GPS SHARKOOL GGPS SHARKOOL GPS DHERI SHARKOOL GPS BELA ZIARAT | 2008-09-10 | 2009-09-09 | 2009-09-09 | 0 55 42 54 4 3 41 59 100 | 40 | 100% | 2009-02-02 14:24 | 2010-05-31 | 76.82%
|  |  |  | GPS DHAMBORI GPS LACHI MANG GPS HAR NAKKA GGPS MAHALLAH MUDASAR GPS RAITRA GGPS SHAKOORA GGPS LACHI MANG GPS Shakoora GGPS Bai Bala | 2008-09-10 | 2009-09-09 | 2009-09-09 | 8 60 59 100 57 3 60 0 58 | 45 | 100% | 2009-02-20 19:12 | 2010-05-31 | 73.92%
45 | M/s Riaz & CO | PERRA/AGRI-02/KOHISTAN/09/2008 | 8 | Tehsil Agriculture Office Pattan | 2009-06-09 | 2010-06-08 | 2010-06-08 | 9 | 9 | 97.8% | 2009-07-11 18:14 | 2010-05-31 | 88.8% | Recommendation for termination sent to client for concurrence vide our letter No 2778/334/JK/11-A/12322 Dated 27-03-2010
|  | PERRA/L.STK.04/ KOHISTAN/08/2008 | 9 | VETERINARY DISPENSARY DUBAIR BALA | 2009-06-09 | 2010-06-09 | 2010-06-09 | 0.67 | 0.67 | 97.53% | 2009-06-11 10:42 | 2010-05-31 | 96.86% | Recommendation for termination sent to client for concurrence vide our letter No 2778/334/JK/11-A/12324 Dated 27-03-2010
|  | PERRA/ LIVESTOCK.03/ KOHISTAN/07/ 2008 | 10 | VETERINARY DISPENSARY SANAGAI | 2009-06-09 | 2010-06-09 | 2010-06-09 | 2.36 | 2.36 | 97.53% | 2009-06-17 14:44 | 2010-05-31 | 95.17% | Recommendation for termination sent to client for concurrence vide our letter No 2778/334/JK/11-A/12323 Dated 27-03-2010
46 | M/s Sabeeb ur Rehman | PERRA/Abbottabad/114/2009 | 26A | GGPS Phelwan GPS Jogi Maira | 2009-11-24 | 2010-11-23 | 2010-11-23 | 6 4 | 5 | 51.65% | 2009-12-12 04:48 | 2010-05-31 | 46.65% | Recommended for Termination
47 | M/s Saifullah Umer Khalil Construction Co. | PERRA/Abbottabad/64/2009 | 97 | GPS ShaheedAbad | 2009-05-02 | 2010-05-01 | 2010-05-01 | 35 | 35 | 100% | 2009-09-06 09:36 | 2010-05-31 | 67.66% | Recommended for LDs
|  | PERRA/Abbottabad/62/2009 | 91 | GGPS Raily | 2009-05-02 | 2010-05-01 | 2010-05-01 | 53 | 53 | 100% | 2009-11-10 22:05 | 2010-05-31 | 51.04%
48 | M/s Sajjad Akhtar & Co. | PERRA/Abbottabad/57/2009 | 42,43 | GGPS Hiran GPS Dheri Hotar GPS Bandiali GPS Pehalwan | 2009-04-22 | 2010-04-21 | 2010-04-21 | 25 35 35 34 | 32 | 100% | 2009-08-16 11:31 | 2010-05-31 | 71.17% | Recommended for LDs
|  | PERRA/Abbottabad/72/2009 | 139 | GMS Nawashehr | 2009-08-06 | 2010-08-05 | 2010-08-05 | 29 | 29 | 81.87% | 2009-11-19 13:26 | 2010-05-31 | 52.87%
49 | M/s Saleh Ejaz & Co. | Bakot Lahoor Road (Khushi Kot - Lahoor) | Single Package | Bakot Lahoor Road (Khushi Kot - Lahoor) | 2009-01-25 | 2011-01-24 | 2011-01-24 | 22 | 22 | 67.35% | 2009-07-04 09:07 | 2010-05-31 | 45.35%
|  | PERRA/Abbottabad/32/2007 | 15C | GPS Bat Nara GPS Nagri Tutial GPS Gambeer # 1 | 2008-03-14 | 2009-03-13 | 2009-03-13 | 48 85 74 | 69 | 100% | 2008-11-20 03:50 | 2010-03-09 | 65.36% | Terminated vide letter No 8962/4-C Dated 09-03-2010
50 | M/s Shahnawaz Khan & Sons | PERRA/Abbottabad/75/2009 | 127B | GPS Mukdabi GPS Zaro Gali | 2009-11-09 | 2010-11-08 | 2010-11-08 | 2 19 | 11 | 55.77% | 2009-12-19 00:58 | 2010-05-31 | 44.77% | Recommended for termination
|  | PERRA/Kohistan/ 04/2009 | H-4 | BHU Sherakot | 2009-06-08 | 2010-06-07 | 2010-06-07 | 7 | 7 | 98.08% | 2009-07-03 11:31 | 2010-05-31 | 91.08% | Recommended for Termination (case is in process to be sent to client)
51 | M/s Shangla Construction Co. | PERRA/Abbottabad/71/2009 | 125-A 125-B | GPS Mallah GPS Salwala | 2009-06-17 | 2010-06-16 | 2010-06-16 | 16 34 | 25 | 95.6% | 2009-09-16 | 2010-05-31 | 70.6% | Recommended for termination
|  | PERRA/Abbottabad/83/2009 | 25B | GPS Lari GPS Barwala GPS Chamiali GPS Gahiar | 2009-08-06 | 2010-08-05 | 2010-08-05 | 22 4 24 8 | 15 | 81.87% | 2009-09-29 14:24 | 2010-05-31 | 66.87% | Recommended for LDs
52 | M/s Shoukat Khan & Co. | PERRA/Battagram/07/2007 | 7 | GPS Barkaley/Mangane Kalay Sijbair GPS Sajbair | 2007-12-07 | 2008-12-06 | 2009-07-05 | 67 67 | 67 | 100% | 2008-12-26 22:05 | 2010-05-31 | 57.4% | Recommendations for LDs have been sent to Client.
|  | PERRA/GOV-Shangla/01/ 2007 | 1-G | T-Office Chakesar T-Residence Chakesar T-Office Puran T-Office Besham T-Residence Besham Civil Judge Res.Alpurai | 2007-11-14 | 2008-10-30 | 2008-10-30 | 42 70 40 68 55 59 | 56 | 100% | 2008-05-28 13:26 | 2010-05-31 | 78.84%
53 | M/s SMS & Co. | PERRA/MAN/94/2008. | 39 | 1 GGCMS Shang Ratta 2 GGPS Chandni 3 GPS Harori Bala | 2009-04-15 | 2010-04-14 | 2010-04-14 | 50 64 8 | 41 | 100% | 2009-09-11 05:46 | 2010-05-31 | 63.69%
54 | M/s TAHIR KHAN&CO, | PERRA/Abbottabad/29/2007 | 7B | GPS Drair | 2008-03-14 | 2009-03-13 | 2009-03-13 | 67 | 67 | 100% | 2008-11-12 21:07 | 2010-05-31 | 69.82% | Recommended for LDs
55 | M/s Umer Daraz Khan | PERRA/Abbottabad/105/2009 | 86 | GGPS Shaqiqa GGPS Rich Bhen | 2009-09-25 | 2010-09-24 | 2010-09-24 | 17 35 | 26 | 68.13% | 2009-12-28 15:22 | 2010-05-31 | 42.13%
56 | M/s Umer Rehman & Co | PERRA/AGRI- 04/ KOHISTAN/11/2008 | 6 | Tehsil Agriculture Office Dassu | 2009-06-02 | 2010-06-02 | 2010-06-02 | 19 | 19 | 99.45% | 2009-08-10 08:24 | 2010-05-31 | 80.45%
|  | Man/86/2007 | 77 | 1) GPS Banda Feroz Khan 2) GGPS Hawa Gali | 2009-05-12 | 2010-05-11 | 2010-05-11 | 72 72 | 42 | 100% | 2009-10-11 21:07 | 2010-05-31 | 60.19%
|  | PERRA/Shangla/13/2007 | 1-B | GHS Titwalan | 2008-03-18 | 2009-03-17 | 2010-01-03 | 54 | 54 | 100% | 2009-03-07 05:46 | 2010-05-31 | 55.94% | Recommendations for imposition of LDs are sent to Client vide our letter No. 2778/334/JK/11-A/11294 dated February 17,2010
|  | PERRA/AGRI- 04/ KOHISTAN/11/2008 | 6 | Tehsil Agriculture Office Dassu | 2009-06-02 | 2010-06-02 | 2010-06-02 | 19 | 19 | 99.45% | 2009-08-10 08:24 | 2010-05-31 | 80.45%
|  | PERRA/GOV-Shangla/06/2008 | 6 | Police Post Yakhtangi | 2009-06-12 | 2010-06-11 | 2010-06-11 | 2 | 2 | 96.98% | 2009-06-19 06:43 | 2010-05-31 | 94.98%
57 | M/s Walayat Khan Wazir | PERRA/MANSEHRA/5/2009. | 11A | 1) GGMS Jabori 2) GPS Kayyan 3) GPS Mathal 4) GGPS Chelabagh | 2009-05-14 | 2010-05-13 | 2010-05-13 | 60 10 30 70 | 43 | 100% | 2009-10-17 12:29 | 2010-05-31 | 59.03%
58 | M/s Wazir Mohammad Wzir & Co | PERRA/KOHISTAN/03/2006 | 8-A | GGPS Chakai GGPS Moreen GHS Bankad GPS Bankad GPS Bazar Ranolia GHS Jijal GPS Jijal GPS KM Palalo GPS Sanga Kandow | 2007-02-01 | 2008-02-01 | 2008-12-12 | 26.35 29.42 0.18 22.74 12.16 15.39 11.77 26.32 15.48 | 18 | 100% | 2007-06-03 09:36 | 2010-05-31 | 89.93% | Terminated vide letter No 6722/4-C
59 | M/s Workman Const | PERRA/Abbottabad/87/2009 | 33A | GPS Kaseel | 2009-10-03 | 2010-10-02 | 2010-10-02 | 5 | 5 | 65.93% | 2009-10-21 04:48 | 2010-05-31 | 60.93%
60 | M/s Yasin Shah | PERRA/MANSEHRA/133/2009 | 135 | 1. GGPS Sherpur 2. GPS Banda Shekhan 3. GPS Rash Sikandara | 2009-07-29 | 2010-07-28 | 2010-07-28 | 18 50 42 | 37 | 84.07% | 2009-12-10 16:19 | 2010-05-31 | 47.07%
61 | M/s Zafar Iqbal | PERRA/Abbottabad/95/2009 | 16C | GPS Jhafar | 2009-09-25 | 2010-09-24 | 2010-09-24 | 4 | 4 | 68.13% | 2009-10-09 13:26 | 2010-05-31 | 64.13%
62 | M/s MAM International | PERRA/Abbottabad/81/2009 | H-81 | BHU Malkot | 2009-04-14 | 2010-04-13 | 2010-04-13 | 0 | 0 | 100% | 2009-04-14 | 2010-05-31 | 100% | Recommended for termination

## AJK
NON-PERFORMING CONTRACTORS IN AJK (TILL MAY, 2010) (Annexed - B)
S. No | Name of contractor | Contract No | Package No | Facilities | Date of commencement | Date of Original Completion | Revised Completion Date i/c EOT(s) if any | Latest Physical Progress Achieved (% age) | Overall Physical Progress (% age) | Planned Progress (% age) | Date on which the physical progress should have been completed | To Date | Lag (% age) | Remarks
1 | M/s Abaseen Associates | SERRA/BAGH/04/2007 | 5 | GGMS Nathgran GBPS Sher Kotli GBPS Mohara Bathara GBPS Rinyala | 2007-12-10 | 2008-12-09 | 2008-12-09 | 96 95 45 62 | 75 | 100% | 2008-09-08 18:00 | 2010-05-31 | 69.68% | Recommended for LDs
|  | SERRA/Bagh/05/2007 | 10 | GGMS Nakker Sheban GGPS Chamber Bhatakot GGPS Bringban | 2008-02-25 | 2009-02-24 | 2009-02-25 | 25 12 25 | 20 | 100% | 2008-05-08 04:48 | 2010-05-31 | 91.14% | Recommendation for termination sent to client for concurrence vide our letter No.2778/334/JK/11-A/17627, dated 26/5/2010
2 | M/s Abel & Amin Brothers | SERRA/GOV-BAGH/ 05/2008 | 5b | Civil Supply Godown Kahutta Grain Godown Kahutta Grain Godown Gugdaar Session Judge Court Kahutta | 2009-07-18 | 2010-07-17 | 2010-07-17 | 32 32 11 5 | 20 | 87.09% | 2009-09-28 19:12 | 2010-05-31 | 67.09%
3 | M/s Allied Development & Co | Serra/Dru-Mzd/02/2007 | 12 | GGPS Basnara GMS Namli Sayedan (a) GPS Mori Sawan GPS Changla GPS Khairabad GPS Chatter Kalas | 2007-01-05 | 2008-01-04 | 2009-07-18 | 52 52 52 65 92 0 | 52 | 100% | 2008-04-30 | 2010-05-31 | 61.27%
|  | Serra/Rw-ED/09/2007 | 23 | GMS Baglay GGPS Beri Topa GPS Airgali GPS Nambal GPS Beroota | 2007-06-12 | 2008-06-11 | 2008-06-11 | 3 51 31 3 48 | 27 | 100% | 2007-09-18 13:12 | 2009-07-31 | 87.37% | Terminated
3 | M/s Allied Development & Co | Serra/Rw-ED/04/2007 | 21 | GGMS Saracha Banakha GGPS Chiran Syedian GPS Mantra Kayat GPS Chiran Nakkar GPS Upper Jalooth | 2008-01-25 | 2009-01-24 | 2009-01-24 | 44 0 31 1 3 | 20 | 100% | 2008-04-07 | 2009-07-31 | 86.8% | Terminated
|  | Serra/Rw-ED/01/2007 | 1 | GHS Hajeera (Primary section) GGMS Hajeera GGMS Aroonta GGPS Tarakhana GGPS Manjora Kathiara GPS Aroonta GGPS Pirkot Syedian | 2007-02-03 | 2008-02-03 | 2008-02-03 | 51 51 37 69 31 31 31 | 43 | 100% | 2007-07-09 22:48 | 2009-07-31 | 82.73% | Terminated
4 | M/s ASCENT - Structural Concept (JV) | SERRA/Bagh/24/2009 | 51,52,54 & 55 | GGPS Housla Gali GGPS Dal GGPS Kot Kharal GGPS Upper Chatter No. 1 GGPS Jabbarr Panyali GGPS Makhdom Kot GGPS Kot Mohree GBPS Androt Rerrbun MSQ Padar Thairi (Syedan) GGPS Chaknarri GGPS Seri Kalsi Govt. MSQ School Lohar Bela | 2009-07-28 | 2010-07-27 | 2010-07-27 | 20 30 10 30 5 5 3 30 30 30 10 30 | 19 | 84.34% | 2009-10-05 03:50 | 2010-05-31 | 65.34%
5 | M/s Cade Creets Associates | SERRA/DRU-Mzd/06/2007 | 16 | GGPS Sabtan GGMS Pothi GMS Achrail (4+1) GMS Achrail (M1) GGPS Kumarbandi (W) GGPS Kumarbandi (E) GGPS Anwar Sharif | 2007-05-18 | 2008-05-17 | 2009-04-30 | 99 99 99 60 99 52 99 | 87 | 100% | 2009-01-27 07:26 | 2010-05-31 | 44.07%
6 | M/s Erectors |  | 63&96 | GPS Tackhan Bandi G Mosque PS Thala Makri GPS Kalas Kloti GPS Betange GGPS Ratan Seri GPS Damon Jhole GPS Naka Shakar Patian GBPS Masloondi GGPS Damon Jhol GGPS Bela Makri GPS Pukhdam GGPS Gugo Syedian GGPS Mera Mindgran GGPS Ghoter Gherpi GGPS Ghoter Mohrain GPS Gali Khokhran | 2009-02-25 | 2010-02-24 | 2010-02-24 | 40 | 40 | 100% | 2009-07-20 14:24 | 2010-05-31 | 68.35%
7 | M/s Gulzar khan & co | SERRA/DRU-MZD/21/2008 | 21 | GPS Pheelgelan GGPS Khuri Kalgran GMS Chanal Bang (3+1) GMS chanal bang (3+0)U GMS chanal bang (2+0) GMS chanal bang (Lab) GGMS Therian GHS Therian | 2008-02-18 | 2009-02-17 | 2009-02-17 | 0 38 45 45 12 7 0 0 | 18 | 100% | 2008-04-23 16:48 | 2010-05-31 | 92.11%
|  | Serra/Dru-Mzd/09/2007 | 23 & 26 | GPS Kopra GGPS Kopra GBMS Noon Bangla GBPS Bharor GBPS Bandi Pohri | 2007-06-23 | 2008-06-22 | 2008-12-08 | 100 92 65 73 6 | 67 | 100% | 2008-06-14 18:43 | 2009-10-22 | 58.01% | Terminated vide letter No. 7071-81 dated 22/10/2009
|  | SERRA/ DRU/ Mzd 18/2008 | 18 | GPS Fatoot GPS Buchian rahimkot GGPS Prem kot GMS Lower kot | 2009-03-04 | 2010-03-03 | 2010-03-03 | 1 1 1 1 | 1 | 63.74% | 2009-03-07 15:22 | 2009-10-22 | 62.74% | Terminated vide letter No. 6387-96 dated 29/09/2009
|  | Serra/Dru-Mzd/10/2007 | Panjkot | GPS Khawar Mang GPS Cheer Bun GPS Arlian(2+0)L-R GPS Arlian(2+0)L-R GPS Grangan GGPS Numble GMS Nari Jugran GMS Nari Jugran (3+1) GGMS Cheer bun (3+1) | 2008-06-28 | 2009-06-27 | 2009-06-27 | 70 0 52 42 35 42 80 80 99 | 56 | 100% | 2009-01-17 20:10 | 2009-10-22 | 57.62% | Terminated vide letter No. 7060-70 dated 22-10-2009
8 | M/s MLS |  | 46,48,58 & 83 | GGPS Dara Muglan GGPS Mehlum GGPS Chandera GPS Makol GPS Shawai G Mos PS Charoota GPS Lundi Dara GPS Subri GPS Mandrian Achril GPS Nandal GGPS Achril GGPS Kiklot G Mosq. PS Hassan Gallian G Mosq. PS Batangi GPS Majhoi GPS Sari Thotha GGPS Mera Parposa GGPS Mir Bandi GGPS Chaari Langar Pura GGPS Sund Gran Pain GPS Kotli Sarar GGPS Khatar Syedian GPS Tarchala | 2009-02-25 | 2010-02-24 | 2010-02-24 | 40 | 40 | 100% | 2009-07-20 14:24 | 2010-05-31 | 68.35%
9 | M/s Raja Jaber & CO | SERRA/DRU-MZD/60/2008 | 53 | GG Literacy centre Danna(2+0) GG Literacy centre Danna(2+0) GBPS Heriola GBPS Batang Bagla(3+0) GBPS Batang Bagla(2+1) GGPS Dacha(2+0) GGPS Dacha(2+0) | 2009-04-30 | 2010-04-29 | 2010-07-03 | 52 52 22 30 30 52 52 | 41 | 85.08% | 2009-10-22 21:22 | 2010-04-30 | 44.08%
10 | M/s Raja Mumshad & co. | SERRA/Bagh/11/2007/08 | 30 | GBHS Naryola GGHS Naryola | 2008-06-18 | 2009-06-17 | 2009-06-17 | 31 33 | 32 | 100% | 2008-10-12 11:31 | 2010-04-30 | 82.9%
|  | SERRA/DRU-MZD/53/2008 | 67 | GPS Kiati GPS Kontal Nar GPS Seri Tarala | 2009-04-10 | 2010-04-09 | 2010-04-09 | 22 45 1 | 23 | 100% | 2009-07-02 17:17 | 2010-04-30 | 78.25%
11 | M/s Sadat Builders | SERRA/DRU-MZD/59/2008 | 65A&66 | GGPS Kangeer Makalan GGPS Pakhan GPS Bahurian GHS Timbi (10+0) GHS Timbi (Multipurpose Hall) GHS Timbi (3Lab+1Lib) GHS Timbi (Admin) | 2009-04-15 | 2010-04-14 | 2010-04-14 | 20 1 7 22 5 5 15 | 11 | 100% | 2009-05-25 00:58 | 2010-04-30 | 89.46%
12 | M/s Shoukat Khan & Co. | SERRA/BAGH/03/2007 | 11 | GGMS Mera GGPS Pandhi GGPS Googlyni Nakker | 2007-10-01 | 2008-09-30 | 2008-09-30 | 16 6 11 | 11 | 100% | 2007-11-10 03:36 | 2010-05-31 | 95.87% | Recommended for termination (case is in process to be sent to client)
13 | M/S Techni Style Engineers | SERRA/ DRU/ Mzd 13/2007 | 13 | GPS Raheel GPS Chooni GPS Battangi Darra GGPS Sarian GGPS Charoota GGMS Lohar Gali GHS Brarkot (H1) GHS Bararkot( M1) GHS Bararkot( 2+0) | 2008-01-25 | 2009-01-24 | 2009-01-24 | 55 55 95 24 3 5 60 55 60 | 48 | 100% | 2008-07-18 04:48 | 2010-04-30 | 78.79%
|  | SERRA/DRU-MZD/29/2007 | 29 | GPS Badhar Bakal GGPS Doombi GGPS Mera Janki GHSS Jandgran (Acadamic Block) GHSS Jandgran (3+1) GHSS Jandgran (3+0) | 2008-02-13 | 2009-02-12 | 2009-02-12 | 5 5 5 20 18 22 | 13 | 100% | 2008-03-31 10:48 | 2010-04-30 | 94.12%
|  | Serra/Dru-Mzd/04/2007 | Noora seri | GPS Gawari GBPS Choon GGPS Bakriali GGPS Chalpani GGPS Nakashakrapattian GGPS Choon GMS Noora Seri 2+0(T) GMS Noora Seri 2+0(T) GMS Noora Seri 3+1 GMS Noora Seri (lab) | 2008-05-17 | 2009-05-16 | 2009-11-17 | 5 15 0 52 5 5 22 22 22 22 | 17 | 95.26% | 2008-08-18 07:55 | 2009-10-22 | 78.26% | Terminated vide letter No 7108-18 DATED 22/10/2009
14 | M/s Umer Rehman & co | SERRA/Bagh/13/2007 | 19 | GBHS Kahna Mohri | 2008-06-18 | 2009-06-17 | 2009-06-17 | 47 | 47 | 100% | 2008-12-06 01:55 | 2010-05-31 | 75.97%
|  | Serra/Rw-ED/18/2007 | 25 | GGMS Ghail Tain GGPS Badoon Pachiot | 2008-04-18 | 2009-04-17 | 2009-04-17 | 0 20 | 10 | 100% | 2008-05-24 09:36 | 2010-05-31 | 95.29% | Recommendation for termination sent to client for termination vide letter No 2778/334/JK/11-A/1113 Dated 29-08-2009
|  | Serra/Rw-ED/20/2007 | 19 | GGMS Chamb Singola GGPS Daban Singola | 2008-06-24 | 2009-06-23 | 2009-06-23 | 28 50 | 39 | 100% | 2008-11-12 23:02 | 2010-05-31 | 79.89% | Recommendation for termination sent to client for termination vide letter No 2778/334/JK/11-A/1114 Dated 29-08-2009
|  | Serra/Rw-ED/21/2007 | 11 | GGPS Gala PirKot GGPS Markazi Pir Kot | 2008-05-15 | 2009-05-15 | 2009-05-15 | 25 25 | 25 | 100% | 2008-08-14 06:00 | 2010-05-31 | 87.77% | Recommendation for termination sent to client for termination vide letter No 2778/334/JK/11-A/1115 Dated 29-08-2009
15 | M/s Zain-ul-abdeen & Sons. | SERRA/BAGH/06/2007-08 | 16 | GBMS Koterri Qandeel GGMS Koterri Qandeel GGMS Badhiar Dharray | 2007-11-15 | 2008-11-14 | 2008-11-14 | 44 50 48 | 48 | 100% | 2008-05-08 04:48 | 2010-04-30 | 80.47% | Recommended for LDs
16 | M/s ZOOM Engineers | SERRA/BAGH/02/2007 | 13 | GGPS Diar Gali GGPS Lahori | 2007-03-28 | 2008-03-27 | 2008-03-27 | 78 25 | 52 | 100% | 2007-10-03 19:12 | 2010-04-30 | 83.19%